## Slide 1
MGC Curriculum Development
MassHire & La Colaborativa: Digital Education Project Plan

## Slide 2
Course | Developer | Hours For Development | Course Duration | Draft Completion for Internal Review | Last Internal Revision Date | Deliverables Due
Data Management/ Storage/Cloud | Nelson | 40 | 12 weeks (12 sessions) | 7-Aug-25 | 14-Aug-25 | 15-Aug-25
Basic Graphic Design | Pablo | 40 | 12 weeks (12 sessions) | 11-Sep-25 | 18-Sep-25 | 19-Sep-25
E-commerce & Digital Marketing | Paola Delgado (?) | 40 | 8 weeks (8 sessions) | 25-Sep-25 | 2-Oct-25 | 3-Oct-25
E-Learning | Catherine | 40 | 8 weeks (8 sessions) | 09-Oct-25 | 16-Oct-25 | 17-Oct-25
Touch Typing | Catherine | 30 | 4 weeks (8 sessions) | 4-Dec-25 | 11-Dec-25 | 12-Dec-25
Calendar Proposal